## Sheet1
CMPT 275 Work Assignment Document
Group 11 - Team Invincible
Group Members: Jia Hui (Mandy) Xiao, Gary (Sheung Yau) Chung, Zavier Aguila, John Kyung Joon Ko, Ryan Kiew Ruelt Yean
| All features listed in the proposal | Version 1 |  | Version 2 |  | Version 3 |  | Comments
|  | Original Plan | Delivered On | Original Plan | Delivered On | Original Plan | Delivered On
Functional Requirements | Register/Login Page
| F1 |  |  |  |  | X
| F2 |  |  |  |  | X
User Registration
| F3 |  |  |  |  | X
Home Page
| F4 | X | 2017-11-05 |  |  |  |  | On schedule.
| F5 |  |  | X | 2017-11-16 |  |  | On schedule.
| F6 |  |  |  |  | X
| F7 | X | [5 empty] | Delayed due to unforeseen bugs during implementation. Settings would not save after changing.
Experience Viewer
| F8 | X | [5 empty] | Delayed - root cause due to failure of implementation of F7. Settings would not save after changing.
| F9 | X | 2017-11-02 |  |  |  |  | On schedule.
| F10 | X | 2017-11-02 |  |  |  |  | On schedule.
| F11 | X | 2017-11-02 |  |  |  |  | On schedule.
| F12 | X | 2017-11-05 |  |  |  |  | On schedule.
| F13 | X | 2017-11-02 |  |  |  |  | On schedule.
| F14 | X | 2017-11-05 |  |  |  |  | On schedule.
| F15 | X | 2017-11-06 |  |  |  |  | On schedule.
Experience Editor Start Page
| F16 |  |  | X | 2017-11-16 |  |  | On schedule.
| F17 |  |  | X | 2017-11-16 |  |  | On schedule.
| F18 |  |  |  |  | X
| F19 |  |  | X
| F20 |  |  | X
| F21 |  |  | X | 2017-11-18 |  |  | On schedule.
| F22 |  |  | X
| F23 |  |  | X | 2017-11-02 |  |  | On schedule.
| F24 |  |  |  |  | X
| F25 |  |  |  |  | X
| F26 |  |  |  |  | X
| F27 |  |  |  |  | X
| F28 |  |  |  |  | X
Non-functional Requirements | Accessibility
| REQ1 |  |  |  |  | X
| REQ2 |  |  |  |  | X
Performance Requirements
| REQ3 |  |  |  |  | X
| REQ4 |  |  |  |  | X
| REQ5 |  |  |  |  | X
| REQ6 |  |  |  |  | X
| REQ7 |  |  |  |  | X
Hardware Requirements
| REQ8 | X | 2017-11-06 |  |  |  |  | App is developed for the iPad platform.